## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Software Engineering |  |  |  |  | COMPANY NAME | [6 empty] | The Poor Students of Towson University
PROJECT MANAGER |  | Megan McCulley, Matt Johnson |  |  |  |  | DATE | [6 empty] | 2018-03-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Gathering Requirements | All | 2018-02-26 | 2018-03-13 | 17 | 0% | bar: WEEK 1 F to WEEK 2 T
1.1 | Use Cases and Sequence Diagrams | All | 2018-02-26 | 2018-03-06 | 10 | 0% | bar: WEEK 1 F to WEEK 2 T
1.1 | High Level Architecture Diagram | All | 2018-03-06 | 2018-03-13 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
1.1 | Class Diagram | All | 2018-03-06 | 2018-03-13 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
1.1 | Interface Spec | All | 2018-03-06 | 2018-03-13 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
2 | Basic Website Functions
1.1 |  |  | 2018-03-12 | 2018-03-15 | 3 | 0% | bar: WEEK 1 F to WEEK 2 T
1.1 |  |  | 2018-03-12 | 2018-03-15 | 3 | 0% | bar: WEEK 1 F to WEEK 2 T
1.1 |  |  | 2018-03-12 | 2018-03-15 | 3 | 0% | bar: WEEK 1 F to WEEK 2 T
2 | Donations Page
1.2 | Basic Donations Page |  | 2018-03-15 | 2018-03-16 | 1 | 0% | bar: WEEK 2 M to WEEK 2 W
1.2 | API through PayPal |  | 2018-03-15 | 2018-03-16 | 1 | 0% | bar: WEEK 2 M to WEEK 2 W
1.2 | Auto-Generated Thank You Letters |  | 2018-03-15 | 2018-03-21 | 6 | 0% | bar: WEEK 2 M to WEEK 3 W
1.3 | Auto-Generated Requests for Donations |  | 2018-03-16 | 2018-03-22 | 6 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 2 R to WEEK 3 R
2 | Registration Page
1.4 | Basic Registration Page |  | 2018-03-18 | 2018-03-22 | 4 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 M to WEEK 3 R
1.5 |  |  | 2018-03-19 | 2018-03-22 | 3 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 T to WEEK 3 R
1.6 |  |  | 2018-03-23 | 2018-03-23 | 0 | 10% | bar: WEEK 2 M to WEEK 2 T; WEEK 3 F
2 | User Submissions
2.1 | Image Submissions |  | 2018-03-24 | 2018-03-28 | 4 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 M to WEEK 4 R
2.2 | Park Description/Reviews Submissions |  | 2018-03-29 | 2018-04-02 | 3 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 F to WEEK 5 F
2.3 | Consent form |  |  |  | 0 | bar: WEEK 2 M to WEEK 2 T
2.4 | Implentation into Game |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
2
3.1 |  |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
3.2 |  |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
3.2.1 |  |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
3.2.2 |  |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
3.3 |  |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
3.3.1 |  |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
4 | The Game
4.1 | General Game Design |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
4.2 | Website Implementation |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
4.3 | Reporting of Scores |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
4.4 | Social Media Connection |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T

## Sheet2
Subsection | Section
Project Management | Our Website
Requirements Gathering | Our Website
Design and Analysis | Our Website
Site Software Development | Our Website
Testing and Production | Our Website
HTML Design and Creation | Backend Software
Backend Software | Site Software Development
Graphics and Interface | Site Software Development
Content Creation | Site Software Development
Database Implementation | Backend Software
Middleware Devolpment | Backend Software
Secuity Subsystems | Backend Software
Catalog Engine | Backend Software
Transaction Processing | Backend Software
Internal Test | Testing and Production
Integration Test | Testing and Production
Report Generation | Testing and Production
Function Design | Design and Analysis
System Design | Design and Analysis
Fundamental Requirements | Requirements Gathering
Non-functional Requirements | Requirements Gathering

## Sheet3
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Software Engineering |  |  |  |  | COMPANY NAME | [6 empty] | The Poor Students of Towson University
PROJECT MANAGER |  | Megan McCulley, Matt Johnson |  |  |  |  | DATE | [6 empty] | 2018-03-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Design/Layout
1.1 | Gathering Requirements | All | 2018-02-26 | 2018-03-13 | 17 | 0% | bar: WEEK 1 F to WEEK 2 T
1.2 | Use Cases and Sequence Diagrams | All | 2018-02-26 | 2018-03-06 | 10 | 0% | bar: WEEK 1 F to WEEK 2 T
1.3 | High Level Architecture Diagram | All | 2018-03-06 | 2018-03-13 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
1.4 | Class Diagram | All | 2018-03-06 | 2018-03-13 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
1.5 | Interface Spec | All | 2018-03-06 | 2018-03-13 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
2 | Website Buildout/DEvelopment
2.1 | Landing Page |  | 2018-03-12 | 2018-03-19 | 7 | bar: WEEK 1 F to WEEK 2 T
2.2 | Registartion Page |  | 2018-03-12 | 2018-03-19 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
2.3 | Login Page |  | 2018-03-12 | 2018-03-19 | 7 | 0% | bar: WEEK 1 F to WEEK 2 T
2.4 | Donations Page |  | 2018-03-19 | 2018-03-26 | 17 | 0% | bar: WEEK 1 F to WEEK 2 T
2.4.1 | Basic Donations Page |  | 2018-03-12 | 2018-03-16 | 4 | 0% | bar: WEEK 2 M to WEEK 2 W
2.4.2 | API through PayPal |  | 2018-03-15 | 2018-03-16 | 1 | 0% | bar: WEEK 2 M to WEEK 2 W
2.4.3 | Auto-Generated email recipts |  | 2018-03-15 | 2018-03-21 | 6 | 0% | bar: WEEK 2 M to WEEK 3 W
2.4.4 | Auto-Generated Requests for Donations |  | 2018-03-16 | 2018-03-22 | 6 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 2 R to WEEK 3 R
2.5 | User Submissions | bar: WEEK 2 M to WEEK 2 T; WEEK 4 M to WEEK 4 R
2.5.1 | Image Submissions |  | 2018-03-24 | 2018-03-28 | 4 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 M to WEEK 4 R
2.5.2 | Park Description/Reviews Submissions |  | 2018-03-29 | 2018-04-02 | 3 | 0% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 F to WEEK 5 F
2.5.3 | Consent form |  |  |  | 0 | bar: WEEK 2 M to WEEK 2 T
2.5.4 | Implentation into Game |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
3 | Game Buildout/Development
3.1 | General Game Design |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
4 | Implementation
4.1 | Website and game Implementation |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
4.2 | Reporting of Scores |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T
4.3 | Social Media Connection |  |  |  | 0 | 0% | bar: WEEK 2 M to WEEK 2 T